## Sheet1
Milestone | Task | Best | Likely | Worst | Avg | Date | Total Number of Hours | Hours per Week for PES
| Develop and document project plan | 1 | 2 | 2 |  |  | 70.05 | 15
Submit project plan | [5 empty] | 2018-09-20
| Build environment setup | 0.25 | 0.25 | 1 | 0.4
| Git repository | 0.25 | 0.5 | 1 | 0.55
| Initial makefile, main() and framework | 1 | 6 | 16 | 7
| Basic command line prompt and parse | 1 | 4 | 10 | 4.6
| Help function | 0.5 | 2 | 6 | 2.5
Command prompt with help |  | 1 | 3 | 7 | 3.4
| Allocate | 1 | 3 | 7 | 3.4
| Free | 1 | 3 | 7 | 3.4
| Display | 1 | 3 | 7 | 3.4
| Write | 1 | 3 | 7 | 3.4
| Invert | 1 | 3 | 7 | 3.4
| Pattern write | 2 | 6 | 14 | 6.8
| Pattern verify | 1 | 5 | 10 | 5.2
Testing file generation and linking |  | 2 | 7 | 12 | 7
| Execution time measurement | 1 | 4 | 10 | 4.6
Feature complete |  | 2 | 6 | 12 | 6.4
| Final report | 1 | 4 | 10 | 4.6
Submit final report |  | 19 | 64.75 | 146 | 70.05 | 2018-10-22 16:34